## Cover
CMR # :
CONSTRUCTION MANAGER CONTINGENCY MODIFICATION REQUEST
Name of Construction Manager |  |  | DATE:
Project: |  | Project No.: |  | FS-
Origination of Contingency Modification Request
Field Work Order:
Request for Proposal:
Request for Information:
Other:
In compliance with Owner policy OP-B-11-D3, the Construction Manager requests to modify the C.M. Contingency as follows:
description of work
Bid Package(s) Impacted by this CMR:
Was this scope of work a part of the G.M.P. Agreement
If yes, explain:
Cost of the Work
Item# / B.P. | Trade Contractor / Vendor | Amount
| Subtotal: | 0
CM Expenses (Applicable only to Scope Modifications)
| Overhead & Profit: | % | 0
| Insurance Adjustment: | % | 0
| Bond: | % | 0
| TOTAL THIS CMR : | 0
Contingency Summary
Original Construction Mgr. Contingency:
|  | Total Previous CMR's: | 0
|  | Amount of this CMR #: | 0
Contingency Ending Balance :
APPROVALS
| Construction Manager |  | Date
| Architect/Engineer |  | Date
| Owner |  | Date
| FSU - Research Foundation |  | Date

## Detail 1
[9 empty] | C.M.R. | 0
[9 empty] | Revision # | 1
Contingency Modification Request - FSU-Material Research Bldg. | [8 empty] | Date : | 2008-05-15
Extension
REF. | Description | Quantity | Units |  |  |  | Labor | Material | Sub | Total
Cost to Modify Door 150.2 per RFI#98 and F.O.#15
RFI#98 | Change Door 150.2 from Solid Wood to Flush
| Aluminum by VistaWall including door prep for |  | Brkdn: | Alum. Dr. (Mat'l) |  | 1516
| hardware by others |  |  | Prep f/hdwr & install. |  | 300
| Buddy's Glass : |  |  |  | Subtotal : |  |  |  | 1816 | 1816
| Arch. Hardware Products : |  |  |  |  | -400 |  |  | -400 | -400
F.O. #15 | Enlarge Door Opening 150.2 w/additional leaf and
hardware and larger frame
| Buddy's Glass : |  | Brkdn: | 2nd Alum. Leaf (Mat'l) |  | 578
|  |  |  | 2nd Leaf Hardware |  | 309
|  |  |  | Prep f/hdwr & install. |  | 200
[5 empty] | Subtotal : |  |  |  | 1087 | 1087
[9 empty] | Total : | 2503

## Detail 2
[9 empty] | C.M.R. | 0
[9 empty] | Revision # | 1
Contingency Modification Request - FSU-Material Research Bldg. | [8 empty] | Date : | 2008-05-16
[5 empty] | Unit Costs |  |  | Extension
REF. | Description | Quantity | Units | Labor | Material | Sub | Labor | Material | Sub | Total
Field Order #19 - Door Hardware Modifications
Subcontractors:
| Buddy's Glass : | 1 | ls | [5 empty] | 3795 | 3795
| Nelson & Affiliates / Shaffield / AHP : | 1 | ls | [5 empty] | -12815 | -12815
| Subtotal | [7 empty] | Subtotal : | -9020
Subtotal
| Overhead & Profit | 15% | [7 empty] | n/a
[9 empty] | Total : | -9020